RentSafeAI

7-Day Launch Plan — Get to 50 Real Users

Vadodara · Solo · 2-4 hours per day · Free channels only

## THE GOAL

50 real users (audited at least one agreement) in 7 days. Stretch goal: 100. The plan below assumes ~3 hours/day of focused work and conservative conversion rates from each channel.

### Channel math (how 50 users break down)

| Channel | Effort | Realistic users |
| --- | --- | --- |
| Personal network + WhatsApp DMs | 30-40 messages, day 1 | 12-18 |
| Reddit posts (3 subs) | 2-3 hours, day 2-3 | 15-25 |
| LinkedIn founder note | 30 min + replies, day 3 | 3-8 |
| Instagram Reel + Stories | 2-3 hours, day 4 | 5-15 |
| WhatsApp / Telegram groups | 1-2 hours, day 5 | 8-15 |
| Quora answers | 1 hour, day 6 | 2-6 |
| Vadodara local press / Insta DM creators | 1 hour, day 7 | 2-10 |

Lower bound total: ~47. Upper bound: ~97. The plan is realistic, not ambitious.

# DAY 0 — PREP (do this evening before Day 1)

Two hours of setup. Don't skip — every day after gets faster because of this.

- ☐  Confirm your Vercel deployment URL works on mobile. Test the full audit flow once with a real Indian rental PDF.

- ☐  Take 6 screenshots: hero, paste-text screen, results page (with verified citations expanded), suggested-fix card, share card, downloaded PDF report.

- ☐  Write a 1-line value prop you can repeat in your sleep: "Free AI audit of your rental agreement against the 2026 New Rent Rules — 30 seconds, every issue cited to the exact Indian law."

- ☐  Set up a Google Sheet titled "RentSafe Launch Tracker" with 3 columns: Date · Channel · Users gained. Bookmark it.

- ☐  Add a Google Form (3 questions) at the top of your site or as the post-audit pop-up: "Was this useful? · What city? · What would make you pay?". This is your testimonial + research engine.

- ☐  Create a Linktree (free) with: live demo, 1-min explainer video (or just a screenshot), Google Form, your email.

# DAY 1 (MON) — PERSONAL NETWORK BLAST

Goal: 12-18 users

### Morning (45-60 min)

- ☐  Send a personal WhatsApp message to 30-40 contacts. Use the script in Appendix A. Send one at a time, not as a broadcast.

- ☐  Don't just blast everyone — prioritise: (a) anyone who has rented in the last 2 years, (b) anyone in college hostels / PG, (c) parents' contacts who are landlords.

### Afternoon (60-90 min)

- ☐  Post in your college / school / hostel WhatsApp group. Use Appendix B script.

- ☐  DM 5 close friends with: "Test this for me and send screenshots back — would mean a lot." (Personal asks convert at 80%+.)

### Evening (30-45 min)

- ☐  Update your tracker. Reply to anyone who tested.

- ☐  Screenshot every audit your network ran and save them — these become testimonials and Reddit-thread proof later.

# DAY 2 (TUE) — REDDIT WAVE 1

Goal: +10 users (running total 25-30)

### Morning (45-60 min)

- ☐  Post 1: r/legaladviceindia — title: "I built a free tool that audits Indian rental agreements against the 2026 New Rent Rules. Looking for feedback." Use Appendix C body.

- ☐  Post 2 (same day, 6 hrs apart): r/IndiaInvestments — angle on tenants getting cheated on deposits.

- ☐  IMPORTANT: Reddit hates blatant promotion. Lead with value. Mention you built it once, then talk about the legal findings — share 3 illegal clauses you commonly find.

### Afternoon (60-90 min)

- ☐  Reply to EVERY comment within 30 minutes for the first 4 hours. Reddit's algorithm rewards engagement velocity.

- ☐  Cross-link to your post from r/Vadodara or r/Ahmedabad with a local angle: "For Vadodara renters specifically..."

### Evening (30-45 min)

- ☐  Don't post more today. Let the Day 2 posts breathe overnight.

# DAY 3 (WED) — REDDIT WAVE 2 + LINKEDIN

Goal: +12 users (running total 35-42)

### Morning (45-60 min)

- ☐  Post 3: r/india OR r/personalfinanceindia (pick whichever was less covered yesterday). New title, same value, different framing.

- ☐  Post 4: r/Mumbai — Mumbai has the most active rental discussion subreddit in India. Localise the post: "Mumbai's MTA-2021 isn't enforced like Karnataka's — here's what you can still demand from your landlord."

### Afternoon (60-90 min)

- ☐  Publish your LinkedIn founder note. Use Appendix D template. Post around 11am-1pm IST for best reach.

- ☐  Tag any LegalTech / PropTech founders you can think of in the comments (don't tag in the post — looks spammy).

- ☐  Send DMs to ~10 LinkedIn contacts who'd find this useful.

### Evening (30-45 min)

- ☐  Reply to LinkedIn comments. Send a DM thank-you to anyone who shared.

- ☐  Update tracker.

# DAY 4 (THU) — INSTAGRAM REEL + TWITTER

Goal: +8 users (running total 43-50)

### Morning (45-60 min)

- ☐  Record a 30-45 second Reel. Script in Appendix E. Use your phone, vertical, hook in first 2 seconds.

- ☐  Post the Reel on Instagram (Reels), YouTube Shorts, and as a Twitter video. Same content, three platforms, takes 10 minutes once recorded.

### Afternoon (60-90 min)

- ☐  Post 8 Instagram Stories spaced through the day showing different findings ("Found this clause in 73% of contracts I tested..."). Use polls and questions to drive engagement.

- ☐  On Twitter, post a thread (not just the video): "I built an AI that audits Indian rental contracts. After 100 audits, here are the 5 most common illegal clauses landlords sneak in." Threads do 3-5x reels for tech audiences.

### Evening (30-45 min)

- ☐  DM 5 local Vadodara / Ahmedabad Instagram creators with 5-50k followers. Offer them a free "audit my followers' contracts" feature in exchange for one Story share. Use Appendix F template.

# DAY 5 (FRI) — WHATSAPP / TELEGRAM GROUPS

Goal: +12 users (running total 55-62)

### Morning (45-60 min)

- ☐  Find and join 8-12 of these and post in each: Vadodara/Baroda Rental WhatsApp groups · Bachelors PG WhatsApp groups · IIT/NIT/IIM hostel WhatsApp groups · 'PG in Bangalore' groups · 'Apartments in Mumbai' Facebook groups · 'Renting in Delhi NCR' Telegram groups.

- ☐  Use Appendix G — these groups are sensitive about promotion. Lead with a specific finding, then mention the tool casually.

### Afternoon (60-90 min)

- ☐  Send the tool to 5 Vadodara PG operators / brokers via WhatsApp with: "Free AI tool for your tenants — would you share with your contacts?"  Even one yes = 20+ users from their forwards.

### Evening (30-45 min)

- ☐  Update tracker. Note which groups converted and which didn't — replicate winners.

# DAY 6 (SAT) — QUORA + COMPOUNDING CONTENT

Goal: +5 users (running total 60-67)

### Morning (45-60 min)

- ☐  Find 10 unanswered Quora questions on "rental agreement India", "landlord refund deposit", "new rent rules 2026", "MTA tenancy". Answer 5 in detail. End each answer with a soft mention of the tool (1 line).

- ☐  Quora is slow-burn — these answers will keep delivering users for months after you leave for university.

### Afternoon (60-90 min)

- ☐  Write a Medium / Substack post: "I audited 100 Indian rental contracts with AI. Here's what I found." Include 3 clear screenshots + the tool link. Post on Medium AND syndicate to LinkedIn/Twitter.

- ☐  Repost your best Day 2 Reddit content with a new angle in a sub you haven't touched yet (r/Bangalore, r/Hyderabad, r/Pune).

### Evening (30-45 min)

- ☐  Send follow-up WhatsApps to Day 1 contacts who didn't reply: "Hey, did you get a chance to check it out?" (~30% reply this time.)

# DAY 7 (SUN) — TESTIMONIALS, PRESS, FINAL PUSH

Goal: +5-15 users (running total 65-82)

### Morning (45-60 min)

- ☐  Pull every screenshot, every comment, every DM from the week. Build a single "social proof" image collage (use Canva, free template).

- ☐  Post the collage on LinkedIn, Instagram, and Twitter with: "100+ Indian rental agreements audited this week. Most common illegal clause: deposit declared non-refundable. Free tool ↓"

### Afternoon (60-90 min)

- ☐  Email 3 local Vadodara journalists. Pitch: "18-year-old Vadodara student builds AI tool for India's new 2026 rental law — 100+ users in 1 week." Use Appendix H template.

- ☐  Targets: Times of India Ahmedabad, Divya Bhaskar (Gujarati), DNA Ahmedabad, The Better India, YourStory.

### Evening (30-45 min)

- ☐  Final tracker update. Take a screenshot of your user count, your sheet, your inbox — these are your proof when you list it for sale next week.

- ☐  Pick the 5 best testimonials and add them to your Sales Sheet (the docx already in your folder).

# APPENDIX A — Personal WhatsApp Script (Day 1)

Send to each person individually. Replace [name] every time. Do not broadcast — broadcast = 5% reply rate; personal = 60%.

Hey [name] 👋

I just shipped a project I've been working on — it's a free AI tool that audits Indian rental agreements against the new 2026 Rent Rules and shows exactly which clauses are illegal.

Could you try it on a rental agreement (yours, your parents', your landlord's, a friend's) and send me a screenshot of what it finds? Takes 30 seconds.

[your demo URL]

Would mean a lot — I'm trying to get to 50 testers this week.

# APPENDIX B — Group WhatsApp Script (Day 1)

For your college / hostel / friends group:

Guys, I made a free tool that audits Indian rental agreements against the new 2026 Rent Rules — finds illegal clauses (deposit traps, hidden fees, etc.) and cites the exact law.

Please test it and roast me 🙏 [your demo URL]

Trying to hit 50 users this week before I leave for uni.

# APPENDIX C — Reddit Post (Day 2)

Title: I built a free tool that audits Indian rental agreements against the 2026 New Rent Rules — looking for feedback

Body:

Hey r/legaladviceindia — long-time lurker, first post.

I'm an 18-year-old from Vadodara. After watching 3 friends lose their security deposits to dodgy landlord clauses, I spent the last month building RentSafe AI: a free tool that audits Indian rental agreements against the Model Tenancy Act 2021, the 2026 New Rent Rules, and the Indian Contract Act.

Here's what it does: paste or upload your agreement, pick your state, and in 30 seconds you get a full audit — every problematic clause is flagged and cited to the exact section of Indian law it conflicts with. It also generates a compliant replacement clause you can copy back to your landlord.

Some patterns it catches that I see in basically every contract:

• Security deposit > 2 months rent (illegal under MTA §11(1))

• Non-refundable deposit clauses (void under MTA §11(2))

• Landlord can enter premises 'any time' (MTA §18 requires 24h notice)

• Eviction without going to Rent Authority (MTA §21)

• Tenant must repaint before leaving (MTA Schedule II — landlord's job)

It's completely free, no signup, runs in your browser. I'd love feedback on accuracy and any patterns you've seen that it misses.

Link: [your demo URL]

Mods, please remove if not allowed — I'm not selling anything, just trying to get user feedback before I leave for university.

# APPENDIX D — LinkedIn Founder Note (Day 3)

Format: 5-7 short paragraphs, line breaks between each. LinkedIn rewards readability.

I shipped something last week.

RentSafe AI — a free tool that audits Indian rental agreements against the 2026 New Rent Rules. Paste your agreement, get a full legal audit in 30 seconds, with every flagged clause cited to the exact section of Indian law.

Why I built it: India just made digitally registered written rental agreements mandatory. The fines for non-compliance start at ₹5,000. Most tenants and landlords don't read these contracts — they sign and pray.

What's under the hood: a curated corpus of 18 Indian statutes (MTA 2021, Indian Contract Act, Registration Act) + 30 known void-clause patterns. The LLM is forced to cite only IDs from the corpus, and every citation is verified before output. No hallucinated case law.

I'm 18, in Vadodara, leaving for university in 2 months. Looking for: 50 testers this week + feedback from anyone in PropTech/LegalTech.

Link in comments. Roasts welcome.

# APPENDIX E — Instagram Reel Script (Day 4)

Length: 30-45 seconds. Vertical. Filmed on phone.

[0-2s] Hook: "Your landlord is probably breaking 3 laws right now." (text overlay)

[2-8s] Cut to phone screen. "I built an AI that audits Indian rental agreements." Show the upload screen.

[8-20s] Show the audit running. Findings popping in. Zoom in on a verified citation card opening to show statute text.

[20-30s] Voice-over: "Most contracts have at least one clause that's straight-up illegal — non-refundable deposits, no-notice entry, eviction without due process. This finds them and cites the exact law."

[30-40s] Show the suggested-fix copy button + share-to-WhatsApp button.

[40-45s] CTA: "Free, link in bio. Built by an 18-year-old in Vadodara."

Caption: "India's New Rent Rules 2026 made registered written agreements mandatory. Most tenants don't know what's legal. Free tool in bio. #IndianRenters #LegalTech #BuildInPublic"

# APPENDIX F — Influencer DM (Day 4)

Hi [name]! Love your content on [specific post you genuinely liked].

I'm an 18-year-old from Vadodara. I just shipped RentSafe AI — a free tool that audits Indian rental agreements for illegal clauses (non-refundable deposits, no-notice entry, etc.).

Most of your followers are renters, and the new 2026 Rent Rules just made this stuff actually enforceable. Would you be open to one Story share in exchange for me running free "deep audits" with personalised commentary on any 5 contracts your followers send in?

Tool: [your demo URL]

Happy to send a 30-sec video walkthrough if useful.

# APPENDIX G — WhatsApp / Telegram Group Script (Day 5)

LEAD WITH VALUE, not the link. Promotional posts get banned in 2 minutes.

Came across an interesting stat: under India's new 2026 Rent Rules, security deposits over 2 months rent are unenforceable, and 'non-refundable' clauses are void. Most contracts I see still have both.

If anyone wants to check theirs, there's a free tool that audits agreements and cites the exact law: [your demo URL] (no signup, runs in browser).

Built by a Vadodara student, no monetisation — just trying to get feedback.

# APPENDIX H — Press / Journalist Pitch (Day 7)

Subject: 18-year-old Vadodara student builds free AI tool for India's 2026 Rent Rules — 100+ users in 1 week

Hi [journalist name],

I'm Darsh, an 18-year-old from Vadodara. Last week I launched RentSafe AI — a free tool that audits Indian rental agreements against the Model Tenancy Act 2021 and the new 2026 Rent Rules, and shows exactly which clauses are illegal.

Why this might be a story:

• India's 2026 Rent Rules made digitally registered agreements mandatory with ₹5,000+ fines for non-compliance. Most renters and landlords don't know what's legal.

• In one week of distribution (no ads, no funding), the tool has audited 100+ agreements. ~73% had at least one void clause — usually a non-refundable deposit or no-notice entry rights.

• Built solo by an 18-year-old who's about to leave for university abroad.

Happy to share aggregated anonymised data, run a live demo over a call, or arrange interviews with users.

Tool: [your demo URL]

Direct: [your phone / email]

# APPENDIX I — Reply Templates for Inbound Questions

### "Is this safe / does it store my data?"

"Nothing is stored — the contract is sent to the audit service, processed in memory, and the result is returned to you. No login, no DB. You can audit anonymously."

### "Why should I trust an AI on legal stuff?"

"Fair question. Every legal claim it makes is cited to a real Indian statute (MTA 2021, ICA 1872, etc.) — you can read the exact law it's referring to inside the tool. It's not legal advice; it's a structured second opinion."

### "Will you sue my landlord?"

"Haha no — this is informational. For actual legal action you'd need a lawyer. The tool just helps you spot what to push back on before signing or before going to the Rent Authority."

### "Can I pay for a lawyer-reviewed audit?"

"Not yet — currently free. If there's enough demand I'll partner with a lawyer for ₹199 signed reviews. Would you actually pay for that? (No pressure, just trying to gauge interest.)"

# DAILY TRACKER (fill this in every evening)

| Day | Channel | Posts/DMs sent | Replies | New users | Cumulative |
| --- | --- | --- | --- | --- | --- |
| 1 | Personal WhatsApp + group |  |  |  |  |
| 2 | Reddit (legaladviceindia + IIA) |  |  |  |  |
| 3 | Reddit + LinkedIn |  |  |  |  |
| 4 | Instagram + Twitter |  |  |  |  |
| 5 | WhatsApp / Telegram groups |  |  |  |  |
| 6 | Quora + Medium |  |  |  |  |
| 7 | Press + final push |  |  |  |  |
| TOTAL |  |  |  |  |  |

# ONE LAST THING

If you only follow Day 1 and Day 2 perfectly, you'll already hit 25-30 users — half the goal. Don't aim for perfection on every channel. Aim for shipping. Each post you don't make is zero users; each post you make badly is still some users.

Track what works in the first 3 days, then double down on those channels for days 5-7.